## Sheet1
ECIER Foundation
Work Plan
|  |  | 2019/20 | [11 empty] | 2020/21
|  |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
A. Board of Directors
No. | Action Item | Responsible
A.1 | Establish board membership criteria and expectations. | Governance/Fin. | 2019/20 Oct: 31
A.2 | Establish give or get policy. | Governance/Fin. | 2019/20 Oct: 31
A.3 | Perform board gap assessment. | Governance/Fin. | 2019/20 Oct: 31
A.4 | Present membership criteria, give/get policy, and gap assessment results to board of directors. | Governance/Fin. | 2019/20 Nov: 5
A.5 | Create board nomination procedures, policy, and forms. | Governance/Fin. | 2019/20 Nov: 29
A.6 | Present nomination procedures, policy, and forms to board of directors. | Governance/Fin. | 2019/20 Dec: 3
A.7 | Develop board & committee nomination strategy. | Governance/Fin. | 2019/20 Nov: 29
A.8 | Meet with identified candidates for board and cmtes. | Board | bar: 2019/20 Jan
A.9 | Develop board onboarding and mentoring procedure. | Governance/Fin. | 2019/20 Jan: 31
A.10 | Nominate two (2) board members. | Governance/Fin. | 2019/20 Mar: 2
A.11 | Nominate committee members. | Governance/Fin. | 2019/20 Mar: 2
B. Fundraising
No. | Action Item | Responsible
B.1 | Analyze programmatic expenses. | Governance/Fin. | 2019/20 Oct: 31
B.2 | Identify fundraising goal for 19/20 & 20/21 | Governance/Fin. | 2019/20 Oct: 31
B.3 | Develop fundraising strategy with diiverse revenue streams(events, individual, corporate, online). | Fundraising | 2019/20 Nov: 28
B.4 | Present fundraising strategy to board. | Fundraising | 2019/20 Dec: 2
B.5 | Provide f/r training and support for board members. | Fundraising | bar: 2019/20 Jan to 2019/20 Feb
B.6 | Coordinate f/r events and activities. | Fundraising | bar: 2019/20 Mar to 2019/20 Aug
C. Marketing
No. | Action Item | Responsible
C.1 | Develop annual marketing plan. | Fundraising | 2019/20 Nov: 28
C.2 | Develop key messages, talking points, FAQ, elevator speech, quick facts. | Fundraising | 2019/20 Dec: 31
C.3 | Develop monthly communications calendar (includes social media, press releases, website, email blasts, etc.) | Fundraising | 2019/20 Dec: 31
C.4 | Provide communications training to board members. | Fundraising | 2019/20 Jan: 28
D. Program
No. | Action Item | Responsible
D.1 | Establish partnership w/Calumet Tech. | Program | 2019/20 Sep: 30; 2019/20 Nov: 28
D.2 | Create student recruitment materials and strategy. | Spark | 2019/20 Sep: 30; 2019/20 Dec: 31
C.3 | Coordinate kickoff meeting. | Program | 2019/20 Oct: 22; 2019/20 Dec: 31
C.4 | Develop program schedule for 19/20 | Program | 2019/20 Sep: 30; 2019/20 Jan: 28
C.4 | Develop program curriculum. | Spark/Program | 2019/20 Sep: 30; 2019/20 Oct: 15; 2019/20 Jan: 28
C.4 | Coordinate student sessions. | Program | 2019/20 Sep: 30; 2019/20 Oct: 15